Learning Multi-Agent Steering Behavior from Images

# 1.  Summary

This project asks whether an algorithm, rather than a modeler, can discover how agents should move — and whether it can do so starting from a picture. A scene image is parsed by a convolutional network into a structured description, and a reinforcement-learning policy drives every agent in that scene from a local, ego-centric observation. The output is the path each agent walks to its goal.

The scene generator is built and validated (Section 4). The remaining work is four experiment families (Section 5).

# 2.  Scope

Four scope decisions were settled:

| Decision | Value |
| --- | --- |
| Agents per scene | Multiple. Agents avoid obstacles, walls and each other |
| Sensing geometry | From the research statement: 220° field of view, range 22 in a 100×100 world |
| First scenario | Obstacle avoidance, and not restricted to hallway layouts |
| Metrics | Both families — success / collision / timeout rates, and the collision-violation, finish-time and remaining-agent counters used in the existing framework |

# 3.  Approach

A two-stage pipeline. Both stages train from the simulator alone: the renderer emits pixel-perfect labels, and the policy learns from reward. No hand-labeled data and no hand-written steering rules enter the system.

| Stage | Component | Input → Output |
| --- | --- | --- |
| 1 | Scene image | 512×512 PNG |
| 2 | U-Net pixel classifier | image → 6-class label map |
| 3 | Geometry extraction | label map → agent poses, obstacles, walls, regions |
| 4 | Scene instantiation | structured description → simulator state |
| 5 | Ego-centric observation | simulator state → 51 numbers per agent per step |
| 6 | Shared policy (PPO) | observation → (turn, speed) |
| 7 | Synchronous simulation | actions → trajectories |
| 8 | Path rendering | trajectories → paths drawn over the input |

The observation is what carries generality, and what makes the comparison possible. Each agent sees 16 field-of-view sectors reported separately for three entity categories — obstacles, walls, other agents — plus goal distance, goal bearing and its own speed. Distances are clipped and normalized, so the vector never encodes absolute position.

All agents share one policy, matching the homogeneous agent setting of the prior work. Agents step synchronously: every action is computed from the same world state, then applied together.

# 4.  Infrastructure

The scene generator and simulator are complete and validated.

Scene generation. Seven layout families — open, corridor, room, doorway, two-doorway, cul-de-sac, and a plus-shaped crossing. Each scene is written as an RGB image, a label map whose pixel values are class indices, and a JSON ground truth with exact agent poses, obstacle geometry, wall segments and regions.

Validation. Every scene is checked in configuration space before it is written: obstacles are inflated by the agent radius via a Euclidean distance transform, so "a disk of radius R fits here" is exact rather than approximated on a grid. The tightest passage from start to goal is measured and recorded with the scene, giving every sample a difficulty label. Obstacles are placed one at a time with the check re-run after each, so a scene can never be sealed shut.

# 5.  Experiment plan

A null baseline first: a greedy controller that just turns toward the goal at full speed, run on 20 scenes per layout with 4 agents and 3 obstacles. Its success rate falls from 56% on open scenes to 4% on the crossing, so the suite spans a wide range of difficulty and the trivial strategy solves almost none of it.

| Layout family | Greedy success rate |
| --- | --- |
| open | 56% |
| room | 34% |
| two-doorway | 12% |
| doorway | 6% |
| corridor | 5% |
| cul-de-sac | 5% |
| crossing | 4% |

Five experiments follow, numbered in the order they run. Each answers one question.

| # | Experiment | Question | Runs | Weeks |
| --- | --- | --- | --- | --- |
| E1 | Perception robustness | How reliable is the image parser, and what do its errors cost? | ≈45 | 2–3 |
| E2 | Layout transfer | Does a policy work on layouts it never trained on? | 15 | 6–7 |
| E3 | Reward sensitivity | How much does the choice of reward change the learned behavior? | 30 | 8–9 |
| E4 | Crowd size | Does the policy still work with 2, 4, 8 and 16 agents? | 20 | 10 |
| E5 | Comparison with discovered models | How do learned policies compare with the genetically discovered ones? | 10 | 11–12 |

## E1 — Perception robustness

Train the pixel classifier at 128, 256 and 512 resolution and with varying augmentation (colour, line width, background, noise, blur). Then run the same policy on parsed geometry and on exact ground truth. The gap between the two is the cost of perception error, and shows whether effort should go into perception or into the policy.

Multi-agent scenes are the hard case: close agents merge into one outline. Since the generator controls spawn spacing, detection error is plotted against agent distance, which shows exactly where the parser breaks.

Runs: ≈45, across resolution, augmentation and architecture variants.

## E2 — Layout transfer

Train on some layout families and test on all seven, including families never seen in training. Report results per layout and split by bottleneck width, so a narrow-passage failure is not mistaken for a wrongly learned behavior.

Runs: 3 training mixtures × 5 seeds = 15.

## E3 — Reward sensitivity

Learning removes hand-written rules, but the reward is still hand-written. This experiment measures how much that choice matters. Vary the progress term, collision penalty, step cost, agent-collision penalty and a clearance bonus, and record how behavior changes: distance kept from obstacles, willingness to pass between two obstacles, path length against safety. It is the learned-policy version of asking how sensitive genetic search is to its fitness function.

Runs: 6 reward variants × 5 seeds = 30.

## E4 — Crowd size

Train and evaluate with 2, 4, 8 and 16 agents. Report collision violations and finish time next to success rate, and test whether a policy trained at one crowd size still works at another.

Runs: 4 agent counts × 5 seeds = 20.

## E5 — Comparison with discovered models

This is the comparison that motivates the project. Score the learned policies on the same scenarios, metrics and protocol as the existing framework’s obstacle-avoidance models. Then compare the paths, not just the numbers: do the two methods find similar solutions, or different ones?

A second step distils the policy into a small decision tree over the same observation, reporting the rules and the performance lost. If the tree reduces to “steer toward the widest open sector”, that is itself a result: two very different search methods reaching the same behavior.

Runs: 2 protocol conditions × 5 seeds = 10, plus evaluation.

# 6.  Computing resources requested

Perception training needs a GPU. Policy training needs many CPU cores, not a large machine. All numbers below are measured on the current code.

## 6.1  GPU for perception training

The classifier is a small U-Net (1.09M parameters). One run of 60 epochs on 5,000 images at 256×256 takes about 14 hours on 8 CPU threads. A mid-range GPU (T4, A10 or V100) is 20–40× faster, so 20–40 minutes per run. The ≈45 runs of E1 need about 23 GPU-hours; 40 are requested to cover re-runs. An A100-class GPU would not help a model this small.

## 6.2  CPU for policy training

The policy is a small network, so training time is dominated by simulating the environment on CPU. The environment runs at 14,000 agent-steps/s per core; with policy inference and updates, a realistic rate is 4,000–6,000 agent-steps/s. Cost grows roughly linearly with agent count, so the budget is set by how much experience the policy needs, not by how crowded the scenes are.

At 10M agent-steps per run, one run takes about 35 minutes on one core. E2–E5 need 75 runs, about 100 with re-runs, or 60 core-hours; sixteen-agent runs roughly double that, so about 100 core-hours in practice. 300 are requested to leave room. The jobs are independent, so on 32 cores a full sweep finishes in under two hours, which lets an experiment be iterated rather than run once.

## 6.3  Data generation and evaluation

Scene generation runs at 20 scenes/s on one core, under 5 core-hours for the semester. Evaluation (100 episodes × 7 layouts × 5 seeds per condition) takes about 10 minutes per condition, around 20 core-hours in total.

## 6.4  Storage

One scene is 15.4 KB with image, label map and ground truth, so 100,000 scenes fit in 2 GB. Checkpoints and logs add little. 50 GB is requested only to avoid asking again.

## 6.5  Totals

| Resource | Requested | Basis |
| --- | --- | --- |
| GPU-hours | 40 | 45 perception runs × 20–40 min (6.1) |
| GPU class | T4 / A10 / V100 | 1.09M-parameter U-Net at 256×256 |
| CPU core-hours | 350 | 100 policy runs × ~35 min, plus generation and evaluation (6.2–6.3) |
| Concurrent cores | 32 preferred | many short independent jobs |
| Storage | 50 GB | 15.4 KB per scene, plus checkpoints and logs (6.4) |
| Time window | Sept 2026 – Jan 2027 | one semester, ~5 hours/week |

## 6.6  Optional extension — learning directly from pixels

+150 GPU-hours, 3 runs. Listed separately: if the allocation is tight, cut this line first.

The project claims that an explicit perception stage beats learning a policy straight from pixels. Training a convolutional policy directly on 128×128 images would test that claim. It is the only experiment that needs sustained GPU time, since a convolutional policy costs about 100× more per step than the small network used elsewhere: 30–50 GPU-hours per seed, 3 seeds.

# 7.  Software environment

Python 3.11 or newer. The simulator needs only NumPy, OpenCV and Pillow, and runs on CPU. PyTorch is used for the classifier and Stable-Baselines3 for PPO. No licensed software, container registry or external data transfer is needed; every dataset is generated locally.

# 8.  Milestones

| Weeks | Work | Output |
| --- | --- | --- |
| 1 | Scene generator, validation, tests, documentation | done |
| 2–3 | Perception pipeline; E1 resolution and augmentation sweeps | perception metrics; error-vs-spacing curve |
| 4–5 | Multi-agent RL environment; first policies on open layouts | training curves |
| 6–7 | E2 layout transfer across all seven families | per-layout results, both metric families |
| 8–9 | E3 reward sensitivity | behavior-vs-reward table |
| 10 | E4 crowd size | results at 2 / 4 / 8 / 16 agents |
| 11–12 | E5 comparison with discovered models | aligned comparison |
| 13 | Distil the policy into readable rules | rule set and its cost |
| 14 | Write-up | report and figures |

Out of scope this semester: leader-following, moving obstacles, and hand-drawn or photographed inputs.

# 9.  Risks

| Risk | What happens | Mitigation |
| --- | --- | --- |
| Merged agent outlines in perception | Nearby agents blur into one blob; their poses cannot be recovered | Main technical risk. Spawn spacing is controlled, so the failure is measured as a curve early, not discovered late. Circle detection with a fixed radius replaces connected components. |
| Comparison protocol cannot be aligned | E5 gives no like-for-like result | Confirm scenarios and fitness definitions with the advisor early (Section 10). |
| No access to the existing framework’s code | Comparison must use a re-implementation | Document the dynamics alignment and state the limitation. |
| Reward tuning eats time | E3 crowds out E5 | E5 has priority. E3 is capped at six variants; its runs are short and parallel. |
| Limited time (5 hours/week) | Not everything finishes | E5 is the must-finish item. Leader-following is out of scope, not a stretch goal. |

# 10.  Items to confirm with the advisor

- Code access. Can the discovered models run in their original simulator, or must the comparison use a re-implementation? This shapes E5 and is the most urgent item.

- Comparison protocol. Which scenarios and fitness definitions should both methods be scored on?

- Form of the result. Is a trained pipeline plus numbers enough, or should the learned behavior also be reported as readable rules? This decides how much of E5’s distillation step is core.

- Input scope. Synthetic images only, or eventually hand-drawn and photographed scenes? This sets the weight of E1.

# 11.  Deliverables

- A validated multi-agent scene generator and simulator, with documentation and tests — complete.

- A perception module that recovers scene structure from images without manual annotation, with detection error reported against agent spacing.

- One shared steering policy learned from reward alone, evaluated on seven layout families under both metric families.

- A measured account of how much the reward’s design shapes the learned behavior.

- A like-for-like comparison between genetically discovered models and learned policies, including the learned behavior written as rules.

# References

Keller, N., and X. Hu. 2019. "Towards Data-Driven Simulation Modeling for Mobile Agent-Based Systems." ACM Transactions on Modeling and Computer Simulation 29(1):1–26.

Le, H., and X. Hu. 2020. "Extended Model Space Specification for Mobile Agent-Based Systems to Support Automated Discovery of Simulation Models." In Proceedings of the 2020 Winter Simulation Conference, 2233–2244. IEEE.

Le, H., and X. Hu. 2022. "Automated Model Discovery for Steering Behavior Simulation." In Proceedings of the 2022 Annual Modeling and Simulation Conference (ANNSIM ’22), 54–65. SCS.

Raffin, A., A. Hill, A. Gleave, A. Kanervisto, M. Ernestus, and N. Dormann. 2021. "Stable-Baselines3: Reliable Reinforcement Learning Implementations." Journal of Machine Learning Research 22(268):1–8.

Reynolds, C. W. 1999. "Steering Behaviors for Autonomous Characters." In Proceedings of the Game Developers Conference 1999, 763–782.

Ronneberger, O., P. Fischer, and T. Brox. 2015. "U-Net: Convolutional Networks for Biomedical Image Segmentation." In MICCAI 2015, 234–241. Springer.

Schulman, J., F. Wolski, P. Dhariwal, A. Radford, and O. Klimov. 2017. "Proximal Policy Optimization Algorithms." arXiv:1707.06347.

Tai, L., G. Paolo, and M. Liu. 2017. "Virtual-to-Real Deep Reinforcement Learning: Continuous Control of Mobile Robots for Mapless Navigation." In IEEE/RSJ IROS 2017, 31–36.

Tobin, J., R. Fong, A. Ray, J. Schneider, W. Zaremba, and P. Abbeel. 2017. "Domain Randomization for Transferring Deep Neural Networks from Simulation to the Real World." In IEEE/RSJ IROS 2017, 23–30.